## Task
Step | Description | Complexity | Comments | Status
0 | Ensure task is implemented by following the coding patterns and testing guideliness. | Low |  | Done
1.1 | Read the entire trucks table from analytics data zone. Path: /mnt/analytics-data/TFI-AnalyticsData/ | Low | Read path from config. | Done
1.2 | Pass the output of 1.1 from extract method to transform method of the ETL job. | Low |  | Done
2.1 | For each Rule R1 to R5 derive a new table with distributon of occurencies per Manufacturer. Save the results as follows: Manufacturer -> RuleName -> Amount of Rule Occurencies | Mid |  | Done
2.2 | Derive the same distribution as in 2.1 but this time if any of the Rules applies and store with RuleName "R" | Mid |  | Done
2.3 | Pivot the table 2.2 so the RuleName becomes a Column and Sum the Amount | Mid |  | Done
3.1 | Write the final dataset (2.3) to analytics zone of the data lake using the below options: .repartition($"RiskCategory") .write.mode("Overwrite") .option("maxRecordsPerFile", 10000000) .partitionBy("Category") .parquet("/mnt/analytics-data/TFI-ReportsData") | Low |  | Done
4 | Implement unit tests for each transformation 2.1 to 2.6. Implement at least one integration test for the entire processing of the ETL job | Mid | Use testing templates and suggested libraries. | Done
5 | Include this job in Azure data factory orchestration as part of PL_Data_Processing | Low |  | Done
6 | CI/CD: Use the following project for the git repository and deployment pipelines. https://dev.azure.com/ApioTFI/51-DataReports | Low | Use our job deployment scripts as defined in guideliness. | Done